## Slide 1
Update on Systems Transformation
City of Tacoma | City Manager’s Office
Study Session
8/18/2020

## Slide 2: New Items 8/18/2020
Section 1: Anti-Racist focused Budget Development
  9/1 Revenue Update at Study Session
Section 2: Transforming Existing Programs
  8/13 – Presented high-level findings of REAP review to departments
  Mid-September – Second round of employee listening sessions
  9/30 – Departments will respond to feedback and work with OEHR to finalize their Racial Equity Action Plans.
Notes: Section 2
Racial Equity Action Plans Implementation planning will happen from October 1 - December 31, and plans will take effect January 1st, 2021
The time period of focus is the coming biennium, but some departments have set longer term goals in addition to their 2021-2022, which we have encouraged where appropriate.
Employee Listening Sessions Two areas of focus for all groups: 1) Providing safe spaces for people of shared identities to connect and have dialogue about their experiences in the workplace and in general. 2) Offer channels for anonymous feedback that can inform our work on anti-racist systems transformation. To answer the question: "Why are we separating people?" - People of color almost never have dedicated space to discuss issues and experiences unique to them - It is helpful to provide space for White people to discuss race (typically the burden is on people of color to educate white people about the dynamics of structural, institutional, and individual racism)
- The analogy of a therapy/counseling session can be helpful here. One would (ideally) never try to enter into the therapy/counseling session of a loved one/spouse, even though you have a deep relationship with that person. That is a given​. We want to foster meaningful and supportive relationships between ALL of our employees, and that means offering employees what they need and sometimes drawing boundaries around those needs.

## Slide 3: New Items 8/18/2020
Section 3: Current State of TPD Systems
  8/18 – 21CP presented City Council overview of proposed phase 1 work plan for TPD assessment
Section 4: Administrative Changes in TPD
  8/13 – Community outreach on Body Camera Policies (hosted by CPAC)
  8/18 – HR presented draft Chief of Police recruitment plan at Council Study Session
Notes: Section 4
Chief of Police Recruitment (Shelby Fritz)
Further development of Transformation Teams Approach: Planning for community led transformation, identifying internal and external resources, establishing work plan, scoping/prioritizing, developing methodology.
Proposed dates for updates to City Council on status of recruitments:
8/18/2020
9/8/2020
10/6/2020
10/27/2020
11/3/2020
Mid-November: City Council interviews with finalists
Late-November: City Council confirmation of next Police Chief
1/4/2021: New Police Chief begins employment

## Slide 4: Systems Transformation Update
Resolution Section | Status | Recent Accomplishments | In Progress/Up Next | Links
Section 1: Anti-Racist focused Budget Development |  | 3,000 responses to Balancing Act survey Budget workshop on 7/31 (anti-racist emphasis) Priority Based Budgeting evaluation of racial and other equity impacts for general government programs All (400+) budget proposals included analysis of equity impacts & Racial Equity Action Plans (REAP) | 9/1 Revenue Update at Study Session Analysis of Balancing Act survey data by demographic and location breakdowns Evaluation of financial impacts and mitigation approaches through service delivery transformation Proposed budget to Council by 10/6 | 
Section 2: New Policies and Programs / Transforming Existing Programs |  | REAP Review Committee present high level feedback to departments 8/13 Build Accountability Framework: Exec team and all Supervisors assigned to discuss Res. 40622 on 8/11 6 person cross-departmental team completed review of departmental REAPs 8/4 | Final Departmental Racial Equity Action Plans due 9/30 Second round of employee listening sessions (mid-September) Incorporating equity into “ci4i” process improvement Framework Forming Strategic Leadership Team for Transformation Process | 
Section 3: Current State Assessment of TPD Systems |  | 21CP presented proposal and plan to Council 8/18 21CP presented proposal and plan to CPAC 8/10 Contracted with 21 Century Policing (21CP) | Analyzing alignment of staffing study recommendations with transformation opportunities | 
Section 4: Administrative Changes and Process Improvements to Increase Transparency in Policing |  | HR presented draft recruitment plan at Study Session 8/18 Community outreach on Police Body Cameras 8/13 8/10 Asked CPAC for search committee volunteer 8/10 HR collecting requirements for Body Camera positions -updated CMO 8/7 Second Preliminary Training on Newly Adopted 8 Can’t Wait Policies 8/6 | HR will present draft recruitment plan for Chief of Police to CMO 8/12 8 Can’t Wait Practical Training at TPD In Service 9/3 Purchasing and contacting process with AXON; identification of funding sources Negotiations with Police Labor Unions CPAC currently reviewing body camera policies Obama commitments | 
Section 5: Legislative Platform to Transform Institutional Racism |  |  | State-level priorities workshop in late September Draft for Council/Board discussion on November 17 Developing draft legislative agenda for state and federal priorities for 2021 | 
 Planned and in Progress
 Plan under Development
 To Be Developed
*New items in orange text
Links Column Purposely left off of slide at this time
Line indicates bottom of slide when table gets too long
Notes: Overview Comments:
This slide reflects a high-level overview of the 5 sections outlined in resolution 40622, adopted by Council on June 30th, affirming the City Council’s dedication and commitment to comprehensive and sustained transformation of all of the institutions, systems, policies, practices, and contracts impacted by systemic racism with initial priority being given to policing in the City of Tacoma.
At this time, the status indicator refers to our progress in establishing a plan to address each section. Green indicates that a plan is in place and we’ve begun taking action. Yellow indicates that the plan is under development. A red indicator would mean that we need to begin planning.
The next 2 columns represent a list of recent accomplishments and upcoming actions, which will be updated for each study session.
The final 2 columns are still under development, but they will outline any issues or barriers and links to more detailed information about specific topics.
SECTION 1:
Budget Process (Katie Johnston/Reid Bennion)
Outreach:
Present to the City Council on Outreach results August 18th. We held an additional outreach event/interactive workshop last Friday and included a focus on Anti-Racism. 35 people attended the meeting. We closed the online surveys and balancing act on Saturday. Currently over 3,000 responded to the surveys and staff will provide demographic breakdowns and location breakdowns at the study session presentation.
Decision Making:
Continued work to evaluate impacts of financial decisions and mitigation approaches through service delivery transformation.
SECTION 2:
Racial Equity Action Plans (Nick Bayard)
The City kicked off the Racial Equity Action Planning (REAP) by department on June 16th, and each department submitted the first draft of their plan as part of their budget presentations to the City Manager in mid-July. The Racial Equity Action Plan template requires departments to set goals and engage in planning around the first three areas of Tacoma's Equity and Empowerment Framework: 1) The City of Tacoma Workforce Reflects the Community it Serves, 2) Purposeful Community Outreach and Engagement, and 3) Equitable Service Delivery to All Residents and Visitors.
Racial Equity Action planning is intentionally embedded in the budget process in order to prioritize anti-racism in the evaluation of resource allocation for the coming biennium.
A six-person REAP review team representing various departments is working now to provide feedback on each plan, and will also be identifying common challenges, areas where support might be needed, scalable or replicable innovations, and ways to institutionalize accountability and continuous improvement citywide in the coming biennium.
OEHR will be holding a feedback and review session for all departments on August 13th, and the deadline for departments to submit their final REAP to the City Manager is September 30th.
OEHR will create a summary of the Racial Equity Planning process, including key highlights, for the Budget Books by the first week in September​ and will support departments in the implementation of their plans on an ongoing basis.
SECTION 3:
Contract with 21st Century Policing (Who?)
Update
SECTION 4:
Chief of Police Recruitment (Shelby Fritz)
Human Resources will be presenting a draft recruitment plan to the City Manager on August 11.
We are planning a timely, thorough and inclusive process led by a search committee that includes a diverse group of internal and external stakeholders and includes opportunities for input and participation from the community and significant outreach to and recruitment of a diverse pool of potential candidates. Once finalized, the plan will be presented to the City Council and regular updates on the progress of the recruitment will follow.
The search committee will assist in the development of competencies for the position. Green indicates that a plan is in place and we have begun taking actions as an organization. Yellow indicates where a plan is under development, but action is pending. Red would indicate the need to begin planning.
Body Worn Cameras (Tadd Wille)
Body Worn Camera (BWC) Vendor Selection and Contract Negotiations (Estimates: $600K first year, $375K ongoing)
  The CPAC vendor review committee has reviewed and agreed that City staff to begin negotiations with Motorola and Axon
  City Staff plans to select the top vendor and finalize vendor/camera costs in the next two weeks. We will meet the goal of having cameras purchased and delivered by Mid-December
BWC Support Staff
  Representatives from Police, IT, Public Record Office, City Manager’s Office and Human Resources met and are finalizing job descriptions, classifications, and recruitment strategies for the civilian staff needed to implement Body Cameras.
    Civilian Support Staff (Estimates: $440K annually) – Salary & Benefits
      3 Public Disclosure Specialists ($260K): For redaction video services
      1 Computer Support Technician ($90K): For BWC technical services
      1 Police Administrative Support Specialist ($90K): For coordination and reporting
  These positions will be advertised by November 1st and will be filled by Mid-December
8 Can’t Wait (Chief Ramsdell)
TPD policies should be updated to integrate three of the eight recommendations:
  banning chokeholds and strangle holds,
  duty to intervene,
  and require a warning before shooting.
Current policies aligned with the remaining five recommendations.
Timeline:
  June: Best practices research and Union review; approved by chain of command
  July 30th and August 6th: Preliminary training on adopted policies
  September 2nd: Comprehensive/practical training regarding 3 policy changes at fall in-service training
SECTION 5:
Legislative Agenda Items (Anita Gallagher)
The City’s Government Relations team is working on developing the draft legislative agenda for state and federal priorities for 2021. Note: The Government Relations team consists of in-house staff in General Government and Tacoma Public Utilities plus our state and federal contract lobbyists.
Initial thoughts on how we can integrate an anti-racism approach to our advocacy work:
• Include a statement on the legislative agenda stating the City supports legislative efforts that address disparate impacts of systems and institutions on communities of color, and opposes policies that cause direct harm, disadvantage, or otherwise negatively impact the health, well-being, and economic security of people of color. (This is not the final proposed language, but a rough concept.)
• Utilize an anti-racist approach to how we engage in broader legislative advocacy efforts, such as our team’s support of Deputy Mayor Blocker on the Board of the Association of Washington Cities and his recent appointment to the AWC Equity Workgroup. Additionally, Council Member Ushka’s role on the AWC Legislative Priorities Committee provides another avenue by which the City can champion anti-racist policies and work with the Association to advance those priorities.
• Coordinate our federal priorities with the National League of Cities Race, Equity, and Leadership (REAL) initiative that serves to strengthen local leaders’ knowledge and capacity to eliminate racial disparities, heal racial divisions, and build more equitable communities.
• Continue to prioritize funding support for public transit, housing, homelessness programs, and the Low Income Home Energy Assistance Program at the federal level.
• Continue to advocate for Immigration and Customs Enforcement to end the use of private prisons for immigrant detention and instead use available alternatives to detention whenever possible. Support recent actions like the House • Appropriations Committee’s bill that reduces funding for ICE while increasing funding for oversight.
• Advocate for the federal government to reform the immigration system to produce a streamlined path toward citizenship for immigrants and support Deferred Action for Childhood Arrivals (DACA).
• Generally, we will call attention to equity impacts when lobbying for or against policies and funding proposals.

## Slide 5: Next Steps Timeline
Chart: 
| 44061 | 44054 | 44056 | 44056 | 44061 | 44061 | 44061 | 44061 | 44075 | 44076 | 44082 | 44084 | 44088 | 44104 | 44110 | 44110 | 44112 | 44123
 | 100 | -80 | -60 | -40 | 75 | 20 | 50 | -20 | 70 | 40 | -80 | -40 | 100 | -40 | -80 | 70 | 10

## Slide 6: Draft Transformation Timeline
All sections will be informed by community involved processes

## Slide 7: Draft Transformation Timeline
All sections will be informed by community involved processes

## Slide 8
Update on Systems Transformation
City of Tacoma | City Manager’s Office
Study Session
8/18/2020

## Slide 9
OVERVIEW
Resolution 40622 passed on June 30th
Weekly report at Council Study Sessions on 5 sections:

## Slide 10
OVERVIEW
Be it resolved:
That the City Manager is hereby directed to keep anti-racism as a top priority in the process of budget development and prioritize anti-racism in the planning of an economic recovery strategy following COVID-19.
That the City Manager is hereby directed to prioritize anti-racism in the evaluation of new policies and programs, as well as the sustained and comprehensive transformation of existing services, with initial priority being given to policing.

## Slide 11
OVERVIEW
That the City Manager is hereby directed to assess the current state of systems in place at the Tacoma Police Department in consultation with police reform experts, and give specific attention to how current policies and existing studies, agency composition, hiring, promotions, staffing levels, training, and accountability systems align to create just outcomes and use this assessment as a foundation for the work of comprehensive transformation.
That the City Manager is hereby directed to actively seek and implement interim administrative changes and process improvements that can legally be taken immediately to improve transparency and accountability in policing.
That the City Manager is hereby directed to work with the Mayor and City Council to build a legislative platform at the local, state, and federal levels that works to transform institutions impacted by systemic racism for the greater equity and wellbeing of all residents of Tacoma, Washington State, and the United States.